## Slide 1
LN on TN MOBILITY MEASURES
for DISADVANTAGED YOUTH
and YOUNG ADULTS
________________________________________
Task E
Developing a proposal for efficient implementation structures
on the level of project operators of TNC mobility measures
February - October 2013
Leading partner: Italy
Partners involved: PACA (FR), Galicia (ES), Germany, Sweden, Autonomous Province of Trento (IT)
TRANSNATIONAL
COOPERATION
UNIT
Autore:
Busalacchi J.

## Slide 2
WHAT Activities | WHEN Timetable | HOW | WHO Partners involved | OUTPUT
1. Planning and preparation of survey tools | 02/13 | Preparation of survey tools open to comments and validation from partners: Grid for the collection of the features of implementation structures of Nat/Reg. Mob. programs Short questionnaire for Mob. programs project operators | Italy | Draft Working Plan Task E (February 28th); Survey tools proposal.
2. Preliminary survey of programs relevant to the topic | 02-04/13 | Desk analysis of relevant documents on: IdA, LLP – Leonardo da Vinci, Equal, Nat/Reg. programs (calls, application forms, assessment criteria, monitoring and evaluation reports). Collection of info from all partners according to the grid provided. | Italy in cooperation with other members in Task E | Comparative grid of implementation structures
Proposal for activities to be developed under Task E / 1

## Slide 3
WHAT Activities | WHEN Timetable | HOW | WHO Partners involved | OUTPUT
3. Survey of experiences and contributions by Mob. programs project operators | 02-04/13 | Delivery of short Questionnaire for Mobility programs project operators | All network partners | Set of recommendations from Mob. project operators
4. Identification of key elements for a sound implementation structure | 04-05/13 | Desk analysis of Comparative grid of implementation structures and Set of recommendations from Mob. project operators | Italy (with comments and contribution from all partners and Mob. project operators) | Draft document "Key elements for a sound implementation structure"
5. WG Meeting | 06/13 | Discussion and validation of the working document | All Task E partners (with possible involvement of national experts/evaluators and Mob. project operators) | Shared proposal of "Key elements for a sound implementation structure" to be finalized at the 3rd network meeting (10/13)
6. Final Drafting | 10/13 | Amendments on the basis of comments and contributions to the document | Italy | Recommendations ready for discussion and agreement
Proposal for activities to be developed under Task E /2

## Slide 4
Activities | Febr. 2013 | March | April | May | June | July | Aug. | Sept. | October 2013
Planning and preparation of survey tools |  |  |  |  |  |  |  |  | 
2. Preliminary survey of programs relevant to the topic |  |  |  |  |  |  |  |  | 
3. Survey of experiences and contributions by Mob. programs project operators |  |  |  |  |  |  |  |  | 
4. Identification of Key elements for a sound implementation structures |  |  |  |  |  |  |  |  | 
5. WG Meeting |  |  |  |  |  |  |  |  | 
6. Final Drafting |  |  |  |  |  |  |  |  | X
Draft timetable to be developed under Task E

## Slide 5: Survey tools/1 1. Grid for the collection of the features of implementation structures of Nat/Reg. Mob. Programs _________________________________________________________________
Beneficiaries: type of organisation and legal status
National partnership
Local network
Number of transnational partners required
Target group/participants
Eligible actions and costs
Funding (min-max), cofunding
Duration of projects
Duration of mobility stay
Payment/ reimbursement of expenditures and costs scheme
Cost claim procedures
Certificates or recognition of experiences acquired abroad

## Slide 6: Survey tools/2 2. Short questionnaire for Mob. programs project operators __________________________________________________________________
What are the key elements for the success of a mobility project?
What kind of organizations are needed?
What skills the project staff should have?
How can you ensure the sustainability of the project?
How do you apply gender equality in your project?
What suggestions would you give to those who intend to carry out a project of mobility?

## Slide 7: Comments/amendments on tools to be sent by the 8st of March to ISFOL: g.calzolari@isfol.it; transnazionalita@isfol.it Upon receiving your comments, the final versions will be sent to partners as soon as possible. _________________________________ You are kindly asked to fill in the Grid (1) and send the Questionnaire (2) to selected Mob. programs project operators. To identify the IdA project operators please refers to the website http://www.ida-eumap.de/ _____________________________ All contributions have to be sent by the 8th of April to ISFOL: g.calzolari@isfol.it; transnazionalita@isfol.it
Thank you !